## Slide 1
Ms. Melody Jensen
AFCEC/CZOM
11 December 2018
PFOS/PFOA Off-Base Drinking Water Impacts

## Slide 2
PFOS/PFOA Timeline at Ellsworth AFB
Off-Base Drinking Water Well Sampling
Future plans
Overview

## Slide 3: PFC Timeline at Ellsworth
  2011 - PFCs detected at the (FT001) as part of Broad Agency Announcement
  2013 - Remedial Investigation (RI) Funded
  2014 - Limited Site Investigation (SI) Completed at 6 Sites
  2015 - Preliminary Assessment Completed
  2016 - Stage 1 Fieldwork for the RI Completed
  2016 - EPA established lifetime Health Advisory drinking water for
    PFOA/PFOA of 70 ppt
  2016 - Off-Base Private Well Identified & Sampled
  2016 - Alternate Water Supply Provided to Impacted Landowners
  2018 - Stage 2 Fieldwork for the RI Completed
  2018 - SI Fieldwork Completed
  2018 - Off-Base Private Drinking Water Well Survey /Sampling
  Future - Stage 3 Fieldwork & Complete RI

## Slide 4: Off-Base Drinking Water Well Sampling
      Private well sampled in 2016 (99 ppt) and again in 2017 (182 ppt)
    Connected 2 impacted properties to alternate water source
      Off-Base Door to Door Private Well Survey/Sampling
        Phase 1: 18 Sept 2018 – 24 wells sampled
          12 Drinking water wells (9 above EPA Lifetime Health Advisory)
          10 Irrigation wells (8 above EPA LHA)
        Phase 2: 29 Oct 2018 – 27 Drinking water wells sampled
          2 Wells above EPA LHA
        Phase 3: 29 Nov 2018 – 16 wells sampled
          10 Drinking water wells (4 above EPA LHA)
          6 Irrigation wells (2 above EPA/LHA)
      Alternate Water provided to properties above EPA LHA

## Slide 5: Off-Base Drinking Water Well Sampling

## Slide 6: Future Plans
      Finalize the PFOS/PFOA Remedial Investigation for site FT001
      Continue to identify and sample off-base drinking water wells for PFOS/PFOA using the 3-Ps
        Proximity
        Probability
        Pathway
      Continue to provide alternate water to impacted properties
        Provide bottled water until permanent solutions are implemented
        Work with property owners to design/install treatment systems (reverse osmosis) on drinking water wells
        Connect properties to municipal water system if available
        Work with municipal water systems to expand service area or capacity if feasible

## Slide 7: Contact Information
Melody Jensen
AFCEC/CZOM
2125 Scott Dr
Ellsworth AFB 57706
605-385-2677
Melody.jensen.1@us.af.mil